## Group Diary
ItSE Group Work Diary Form
Team #/Name:
Student Name | Email | Work Diary Agreed Tasks
Mateusz Kuzon | c3076381@student.shu.ac.uk | Pln1,Pln3, Pln6,Pln7,Pln11,Imp8,Imp9,Imp10,Tst4
Scott Forster | c3022458@student.shu.ac.uk | Pln1, Pln2,Pln7,Pln8,Pln9,imp2,imp3,imp4,tst2
Charlie Molnar | c3035956@student.shu.ac.uk | Pln1,Pln5,Pln7,Pln10,imp5,imp6,imp7,tst3
Nasir Al-Monsur | c3077195@student.shu.ac.uk | Pln1,Pln4,Pln7,Imp1,tst1
Note: List all tasks seperated by commas for each member.
Phase | Task Id | Task | Predecessor Task | Planned Start Date | Planned End Date | Actual Sart Date | Actual End Date | Status
Planning | Pln1 | define scope | N/A | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2024-10-08 | Done
Planning | Pln2 | Use Case | Define Scope | 2024-10-07 | 2024-10-13 | 2024-10-07 | 2024-10-13 | Done
Planning | Pln3 | ERD | Define Scope | 2024-10-07 | 2024-10-13 | 2024-10-07 | 2024-10-13 | Done
Planning | Pln4 | WireFrames | Define Scope | 2024-10-07 | 2024-10-13 | 2024-10-07 | 2024-10-13 | Done
Planning | Pln5 | User Stories | Define Scope | 2024-10-07 | 2024-10-13 | 2024-10-07 | 2024-10-13 | Done
Planning | Pln6 | Construct Database | ERD | 2024-10-08 | 2024-10-13 | 2024-10-08 | 2024-10-13 | Done
Planning | Pln7 | C4 Diagram | Define Scope | 2024-10-21 | 2024-10-27 | 2024-10-21 | 2024-10-27 | Done
Planning | Pln8 | Personas | User Stories | 2024-10-21 | 2024-10-27 | 2024-10-21 | 2024-10-27 | Done
Planning | Pln9 | Sequence Diagram | Define Scope | 2024-10-21 | 2024-10-27 | 2024-10-21 | 2024-10-27 | Done
Planning | Pln10 | Class Diagram | Define Scope | 2024-10-21 | 2024-10-27 | 2024-10-21 | 2024-10-27 | Done
Planning | Pln11 | Group Work Diary | Define Scope | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2024-10-04 | Done
Implementation | Imp1 | Log In Page | Planning Stage | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp2 | View All Stock | Planning Stage | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp3 | Manage Stock Popup | View All Stock | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp4 | Search/Filter Stock | View All Stock | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp5 | View Cart | View All Stock | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp6 | Checkout Cart - Generate invoice | View Cart | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp7 | Manage Cart | View Cart | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp8 | View All Stock - Administrator Only | View All Stock | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp9 | Administrator View/Manage Employees | View All Stock - Administrator Only | 2024-10-28 | 2024-11-13 | 2024-10-28
Implementation | Imp10 | Administrator Generate Report | View All Stock - Administrator Only | 2024-10-28 | 2024-11-13 | 2024-10-28
Testing | Tst1 | Test Login | Log In Page | 2024-11-13 | 2024-11-17 | 2024-11-13
Testing | Tst2 | Test Stock | View All Stock | 2024-11-13 | 2024-11-17 | 2024-11-13
Testing | Tst3 | Test Cart | View Cart | 2024-11-13 | 2024-11-17 | 2024-11-13
Testing | Tst4 | Test Administrator | View All Stock - Administrator Only | 2024-11-13 | 2024-11-17 | 2024-11-13