## Group Diary
ItSE Group Work Diary Form
Team #/Name:
Student Name | Email | Work Diary Agreed Tasks
Mateusz Kuzon | c3076381@student.shu.ac.uk
Scott Forster | c3022458@student.shu.ac.uk
Charlie Molnar | c3035956@student.shu.ac.uk
Nasir Al-Monsur | c3077195@student.shu.ac.uk
Note: List all tasks seperated by commas for each member.
Phase | Task Id | Task | Predecessor Task | Planned Start Date | Planned End Date | Actual Sart Date | Actual End Date | Status
Planning | Pln1 | define scope | N/A | 2024-10-04 | 2024-10-04 | 2024-10-04
Planning | Pln2 | Use Case | Define Scope | 2024-10-07 | 2024-10-13
Planning | Pln3 | ERD | Define Scope | 2024-10-07 | 2024-10-13
Planning | Pln4 | WireFrames | Define Scope | 2024-10-07 | 2024-10-13
Planning | Pln5 | User Storeis + Acceptance Test | Define Scope | 2024-10-07 | 2024-10-13
Implementation | Imp1 | Construct Database | Planning Stage
Implementation | Imp2 | Log In Page - Front End | Planning Stage
Implementation | Imp3 | Index Page - unlogged in - Front end | Planning Stage
Implementation | Imp4 | Index Page - logged in - Front end | Planning Stage
Implementation | Imp5 | Add Stock - Front end | Planning Stage
Implementation | Imp6 | Remove Stock - Front end | Planning Stage